## Sheet1
Week | <component> | DEV LOE | Actual time
2020-10-01 | Project plan | 4 | 1
2020-10-08 | Create Azure account and subscription | 4 | 0.5
2020-10-15 | Create development environment | 4 | 1
2020-10-22 | Set up Azure Cloud shell | 4 | 2
2020-10-29 | Pull a testing script | 4 | 2
2020-11-05 | Run local tests | 4 | 2
2020-11-12 | Set up Azure Cloud shell | 4 | 4
2020-11-19 | Configure GitHub actions | 4 | 4
2020-11-26 | CD on Azure | 4 | 4
2020-12-03 | Create a README | 4 | 6
2020-12-10 | Create a Demo | 4 | 1
2020-12-17 | Submit project | 1 | 1
| Goals | Goals
Create developnment environment
Create a Flask App
Test the code locally
Complete CI delivery
Complete CD delivery